## Details
EVENT DETAILS
Event Name
Event Date
Event Time
Event Location
Primary WSU Contact
Secondary WSU Contacts
Event Description
Audience
WSU Event Calendar Link
Get Involved Calendar Link
RSVP Link

## RSVP List
RSVP LIST
Date it was last updated

## Run of Show
RUN OF SHOW
Event Time
Time
Welcome
Intro's
Main body of event
Q&A
Closing

## Virtual Logistics
VIRTUAL LOGISTICS
Duty | Coordinating Staff | Status (Not Started, In-Process, & Completed) | Notes
Planning
Add event to Sharepoint (reminder, look for event overlaps)
Confirm date and add event to Dean's calendar
Submit an SSW MAC Event Promo form once planning is complete (https://forms.wayne.edu/60104aff5803e/)
Host pre-event discussion for speakers and moderator at least one week in advance of event
Determine speaker/moderator SSW point-of-contact person
Virtual venue
Obtain Zoom link (reminder, set attendance limit in RSVP to coordinate with Zoom limit)
Coordinate Zoom support staff (detail in Virtul Volunteers tab)
Creating placeholder slide for event that attendees will see when they enter the virtual space
Additional Event Day Coordination
Coordinate virtual faculty and PhD student meeting (includes marketing, obtaining Zoom, launching session)
Coordinate any other private meetings with faculty
Speakers and moderator (detail out what has been otained for who below this chart)
Confirm date and time of lecture and honoarium amount
Create and distribute to speaker itineary and event details to appropriate parties
Coordinate honorarium paperwork and submit
Obtain CE materials (CV, learning objectives, publication refs)
Request approval to record event and share on YouTube and as a future CE course
Obtain MAC materials (event title, full name/credentials, job title, social media handles, event description, 2-3 sentance bio)
Obtain PowerPoints (reminder, ask if we can share with attendees after the event)
Gather question for Q&A from moderator, organizers and RSVP (be sure to send to panelists in advance)
Processes reimbursements
Marketing
Create and distribute promotional materials for the event
Invite other special attendees (donors, BoV, etc..)
Send RSVP reminder email night before event
Coordinate student attendance tracking
Coordinate post-event email with PowerPoints and recommended reads from presenters
Coordinate President or Provost attendence and remarks
Provide bullets notes of items to remember for welcome and closing
CE
Create sign-in link for event in Qualtrics (include CE and student extra credit tracking)
Create post-event evaluation/quiz link in Qualtrics
Obtain Zoom attendance report
Request payment link be added in online store
Send post-event email to attendees with payment eval/quiz link and payment link
Complet and submit CE application

## Virtual Volunteers
VIRTUAL VOLUNTEERS
Task | Volunteer(s)
Launch event
Allow attendees into space from waiting room
Respond to questions in chat
Share CE and student attendance link in chat
Spotlight speakers
Grant speakers co-host access to share screen
Make sure Zoom link has needed features (all attendees muted; muted upon entry; no whiteboard, etc..)

## Virtual Expenses
VIRTUAL EXPENSES
Index
Is this event listed in your annual budget?
Last Budget Revision Date
VIRTUAL EVENT EXPENSES
Expense | Budget | Expenses Paid | Notes
Zoom / online platform
AV services
Honoariums (itemize below) |  | 0
TOTALS | 0 | 0
Itemized Honorariums
Panelist 1
Panelist 2
Panelist 3
Panelist 4
Moderator
TOTAL | 0